## Draft project details
Novel insights into browse preferences with Asian and African tortoises housed in Tortoise Shell-ter |  |  | Accession Number | Research Proposal | Schedule | RP Liaison | Start date | Expected end date | Principal investigator
|  |  | NA | Submitted | NA | Po Han | 2022-06-01 | 2023-06-01 | Jia Yan
Date | Attendees | Status updates / Meeting minutes | Tasks (Section) |  |  | Notes | Placeholder | Placeholder | Placeholder
2022-06-21 |  | 1. Proposal submitted to RP (June) | 1. To share with section / JY 2. To refine this further 3. Arrange for (bi)weekly / monthly catch-ups with PI

## FY2223 (Summary)
Animal Care Research Projects FY2223
Section | Project Title | Principal Investigator | Context and Expected Outcomes | Expected Completion Date | Publication Expected? (Y/N) | RP Liaison (Status unsure) | Accession Number | Status Updates
Inverts | Examining the growth rates of feeder phasmids (e.g., Gray Twigs, Jungle Nymphs and Red Wings stick insects) under varying environmental parameters | Delvin | Aims/ Objectives To identify and examine the necessary environmental parameters for ideal growth in Jungle Nymphs, Gray Twigs and Red Wings stick insects Background / Context At present, very little has been understood on the environmental parameters influencing growth rates of captive stick insects as there is a general dearth of available information on the outcomes of captivity of these species. That said, the invertebrate team in the Singapore Zoo has attained remarkable success in the breeding programmes of these three phasmid species and plans to integrate these species into feeder colonies are currently underway (see WNC projects). Therefore, understanding how growth across instar stages as well as physical morphometrics (e.g., length, size) could be positively influenced through controllable environmental parameters could be beneficial for the establishment of such feeder colonies. Methodology To collect data on the morphometric measurements as well as instar changes of phasmids housed under different environmental parameters Expected outcomes Project outcomes can be written into the corresponding chapter for BPGs and LTMPs of each studied species. | 2023-03-01 | Y (for each BPG) | PH (WNC) |  | - Pilots and preliminary studies ongoing - Proposal on-going
| Comparing the use of native browse species to Alfafa hay with captive tortoises housed in TS | Jia Yan / Jon / Sarah | Aims/Objectives To diversify the diets for captive tortoises through the inclusion of relevant browse species (n = 4) Background / Context Alfafa hay (AH) has been a used a mainstay in the diets of captive grazers. Here, the effects stemming from the inclusion of native browse into captive tortoise diet has not been examined even when anecdotal observations have determined that the exclusion of AH led to an increase in frequency and extent of loose stools in the studied species. In addition, the active non-consumption of AH in tortoises has led to a general increase in husbandry man-hours when keepers are required to trim the provided hay into bite-sized portions so as to encourage consumption. Methodology 1. To compare the preferences towards four different browse species across 3 different species of tortoises housed in TS. 2. Activity budgets and levels as well as fecal scores will be recorded Expected outcomes An improvement towards captive tortoise diets in relation to browse provision / availability. |  | Y | PH (WNC) |  | 1. Proposal submitted 2. Data collection started with intern
| Manipulation of UV spectrums to improve the feeding behaviours of Panther chameleons - External collaboration | Jose/Shaun/ NUS | Aims/Objectives To better understand the range of ideal UV spectrums necessary for improved feeding behaviours and patterns in chameleons Background/Context Although information pertaining to ideal UV spectrums have been reported for captive chameleons, the effects of varying UV intensity and wavelengths on feeding behaviour and patterns of Panther chameleons have not been fully established. Here, the study aims to examine how the manipulation of UV spectrums could enhance or improve the feeding behaviour of the studied animals, and how such manipulations could be integrated to improve on the repertoire husbandry procedures for these animals. Methodology To collect observational data on the feeding behaviour and patterns of Panther chameleons under varying levels of UV. Variations in behavioural and health parameters under the influence of varying UV spectrum would be documented. Expected outcomes A better understanding of the importance of UV gradients, and how such manipulations could be supplementary to chameleon husbandry practices | 2023-03-01 | Y |  |  | 1. In-talks with external lab
| The effects of anthropogenic disturbances (e.g., construction) on the bio-acoustics (e.g., calls) of frogs housed in Fragile Forest - External Collaboration | Shaun/Jose/NUS | Aims/Objectives 1. The effects of construction on the frequency and extent of frog calls will be examined 2. Justifying the use of frog calls as an indicator of welfare through correlation with other established amphibian physiological and (i.e., posture, respiration rate) behavioural responses (e.g., stereotypies) Background/Context The development of captive amphibian welfare indicators is at its infancy stages while the notion of frog calls as a response to captive care has not yet been investigated. In this study, the sporadic occurrence of night renovation works (in the absence of park visitorship) provides a unique opportunity to examine the latent effects on frequency and rate of calls as well as the frogs' physiological responses in the following day. Methodology Specialised acoustic equipment (from NUS) will be used to measure the rate and extent of calls of frogs housed in Fragile Forest. Behavioural responses to construction will also be recorded. Expected outcomes A better understanding on the effects of construction on frog behaviour and a new justifiable approach to examining welfare metrics in amphibians. | 2022-03-23 | Y |  |  | 1. In-talks with external lab
Aquatics | Are our Manatee calf growth rates comparable to wild individuals? | Joan/Jayce | Objectives To compare the growth rates of the manatee calves in the wild with those born in River Safari. Using the data collected, we can publish a paper on how we successfully hand-raise our manatee calves in River Safari by monitoring their growth rates. | 2023-03-01 | Y | Guillaume |  | Waiting on Joan to return from Malaysia for discussion / data analysis.
| The fasting cycles of Mekong giant catfishes in River Wonders | Sandra/Jayce | Objectives To better understand the behavioural and morphlogical shifts in MGCs during their endogenous and seasonal fasting cycles Background/Context For the last three years, coarse-scale behavioural responses stemming from the cyclical pattern of inappetance during the monsoon seasons have been documented. In addition to these behavioural changes, an increase in mouth lesions were also observed but not documented. Here, this study aims to better quantify the consequences of such cycles, and its implication to health and husbandry practices. Methodology A fine-scale focal approach to measuring swimming behaviour and scale discolouration will be adopted to quantify the changes induced from in-appetance. Occurrence and extent of mouth lesions will also be rigorously documented. Expected outcome Educational and outreach signages regarding the occurrence of such mouth lesions will be developed to address visitor concerns. Treatment and prevention of such lesions will be discussed with the veterinary department after the project concludes. | 2024-03-01 | Y | Guillaume? |  | 1. Data received from Sandra 2. In-talks of further expansion end of 2022 3. DJ to start data analysis in Aug.
Avian
Carnivores, Small Mammals & Marsupials | The use of olfactory enrichment on the behaviours of two predator species (Red Dhole & Malayan Tiger) | Najilah/Daniel/Cecilia | Objective To study how different olfactory cues can increase the evenness of enclosure spatial use as well as activity levels in dholes and tigers Methodology Ethogram is prepared for both species. Focal + continuous sampling (all-time occurrence) for the 1.1 Malayan Tigers, Instantaneous/scan sampling at fixed time points will be used for the Red Dholes as they are managd in a group setting and focal sampling can be challenging. Olfactory based mixtures for the study include: 1. Feces 2. Blood 3. Catnip Context / Expected Outcomes Both species will be time-sharing the same flex/enclosure in the new Rainforest Park, hence results can be applied to activity and behavioural management considerations, both now and in future. | 2022-03-23 | KIV after discussion and assessment of publication potential with RAP based on data quality | Cecilia | MWG211002 | 25-Nov-21: Data all collected, will liaise with Dr Shangzhe for data analysis and write up
| Mixed exhibits housing small meso-carnivores in Night Safari | Najilah (University Sains Malaysia Msc programme)/Razzak | Objective 1. To examine the social interaction between small predators (e.g., Small Toothed civets, Common Palm civets, Binturong, Masked Palm civet, leopard cat) housed in mixed exhibits 2. To investigate the role of various types of enrichment devices in mediating agonistic interactions betwee small predators Methodology Ethogram will be prepared for all studied species. Context / Expected Outcomes Understanding the dynamics and interactions between small predators under captive care can be highly beneficial for us as we progress towards the Modern Zoo. Here, the outcomes of said study might inform future husbandry practices in relation to installing and maintaining mixed species exhibit, as well as introducing enrichment ideas that are capable of reducing intra- and inter-social aggression.
| Respiratory rate of tree kangaroos in relation to temperature and humidity | Hafiz/Jeff/Joey/Razzak | Objective To study and obtain data on the respiratory rate of the Tree Kangaroos housed in a tropical environment and its correlation with temperature and humidity Context / Expected Outcomes There are not much data on respiration rates of tree kangaroos in publications. As such we would like this study to shed some light on what is the respiration rate of the tree kangaroos in relation to the temperature, humidity as well as in relation to their age, sex and activity. Methodology 1. Ethogram is essential to identify not only the various behavior but also the spatial selection of the exhibit (e.g., how often under shade). 2. A data logger is needed to collect environmental parameters (temperature and humidity) 3. focal sampling with interval recording of respiration rate 4. Temperature of the TKG's ear, body and forearms will also be recorded 5. Data is collected for: - Adult Female (Nupela) - Young male (Malolo) - Adult Male (Makaia) | Mar-23 At least report or write-up | KIV after discussion and assessment of publication potential with RAP based on data quality | Guillaume |  | Ongoing discussion/preparation Should involve other zoos?
Herbivores | Body Condition Scores of Giraffes (External collaboration) | Ivan/Marcus Clausse | A 3-year long project where photographs of the 4.0 giraffes depicting body condition scores are sent to an external collaborator (e.g., Marcus Clausse). | 2025 | Yes, we get co-authorship from this collaborative effort | DJ |  | Ongoing
| Browse preferences in giraffes | Abigail/Indah/Cynthia/Ivan | Aim/Objective 1. To examine the palatability and/or preference of browse species with the 4.0 giraffes in our collection and, 2. To examine how the provision of varying browse types influences their extent of foraging behaviour. Methods A preference and/or palatibility approach to identify preferred browse species will be adapted for the giraffes Ethograms (through ZooMonitor) will be used to examine activity budgets as well as other behavioural indices (e.g., richness, evenness, diversity) Foraging responses will also be measured and documented. Outcomes This study aims to justify the procurement of preferred browse species through observable enhancement and/or improvement in activity levels and patterns following the | 2022-03-01 | N | Guillaume | N/A
Primates | Group dynamics of baboons before and after population management techniques | Boon Kong (BK) | To study the effects of birth control of the group dynamics of our baboon population. To see if the selective management or contraception impacts the breeding behaviours of the dominant animals in their respective harems. Looking to see if docents or VEU can assist in gathering of data. | Will span over 2-3 years Initial phase 1 completion by Nov-21 (intern base line data gathering) | Y Likely as a paper and/or publication under EAZA old world monkey TAG | Claudia |  | Individuals and troops identified in intern's project
| Optimal efficiency of browse intake by leaf-eating primates | Tiara/BK | Aims/Objectives 1. To examine browse palatability and/or preferences with the Proboscis monkey and, 2. To determine the the change in activity levels and patterns following the introduction of preferred browse species. Methods 1. A palatability and/or preference approach to browse species will be conducted following which, 2. ethograms designed to examine changes in activity levels and/or patterns as well as intra-social group interactions (positive and/or negative) will be employed. Outcomes This will help to not only identify the wastages and look towards optimizing our browse provisions but also provide preferred and more nutritious browse species for the animals under our captive care. This is also, in part, supplementary information that could be used to support the nutrition analyses of browse species conducted with WNC. | 2022-02-01 | N Likely in-house presentation | Po-Han |  | Follow up with Po-Han
| The effects of introducing phasmids as feeder insects to Emperor tamarins | Xiao Jun/Kelly/Kumaran | Aims/Objectives 1. To examine palatability and/or preferences of phasmids with the Emperor tamarins and, 2. compare their use to commercial feeder insects (e.g., crickets, mealworms) through changes in behavioural and spatial responses. Methods 1. Ethograms designed to examine changes in activity levels and/or patterns as well as intra-social group interactions (positive and/or negative) following the introduction of phasmids and commercial feeder insects will be used. Outcomes The outcomes of this study is aimed at improving the repertoire of foraging behaviours in Emperor tamarins through the provision of phasmids as feeder insect. In addition, the nutritional analyses of phasmids can be supplementarily used to identify chemical factors that best explains the changes in activity levels and patterns. | 2022-02-01 | N Likely in-house presentation | Po-Han |  | Follow up with Po-Han
| The effects of nightly heat lamps on the diurnal activity patterns and levels of Celebes monkeys | Xiao Jun/Kumaran | Aims/Objectives 1. To examine how the inclusion of heat and/or fog lamps at night could have an effect on the resting behaviour of Celebes monkeys through next-day activity patterns. Methods 1. Ethograms designed to examine the activity levels and patterns of these primates will be used to observe and monitor the studied animals in the exhibit as well as the back of houses. 2. Environmental parameters such as temperature and humidity will also be recorded Outcomes Understanding the influence of heat lamps on sleep cycles or resting behaviour is crucial for manging their next-day activity levels and patterns. The outcomes of this study can and will be used to improve the husbandry procedures related to these primates. | 2023-04-01 |  |  |  | Data collection
| Orangutan Weight-by-age Growth Chart | Xiao Jun/Kumaran | General information on the weights of orangutans is often provided as a range, mostly for the wild counterparts in the adult stage of growth. There is an apparent void of written information on the weight range expected for orangutans at their different stages and years of growth. The analysis of weight data of captive specimens to construct a weight-by-age growth chart will be a helpful tool, especially for the monitoring of health and consequently, welfare of the animals under human care. The chart could work together with data from body condition scoring to help provide a healthy weight range for staff to manage the animals at, building up our knowledge and expertise in caring for these great apes. |  |  | Guillaume |  | Unknown
Wildlife Nutrition Centre | The nutritional analysis of (feeder) insects (e.g., phasmids, blue worms) | Po Han | As part of a inter-disciplinary project, the information obtained from this reseach component will be used to feed in the various projects designed to examine the palatability and/or preference of phasmids / blue worms and the influence these insects have on activity and behavioural patterns.
Wildlife Nutrition Centre | Examining the growth rates of blue worms kept under varying levels of environmental parameters and food type. | Po Han | As part of a inter-disciplinary project, the information obtained from this reseach component will be used to feed in the various projects designed to examine the palatability and/or preference of phasmids / blue worms and the influence these insects have on activity and behavioural patterns.
Giant Panda
Rainforest KidzWorld
Elephants

## FY2223
Animal Care Research Projects FY2223
Section | Project Title | Principal Investigator | Context and Expected Outcomes | Expected Completion Date | Publication Expected? (Y/N) | RP Liaison (Status unsure) | Accession Number | Status Updates
Inverts | Examining the growth rates of feeder phasmids (e.g., Gray Twigs, Jungle Nymphs and Red Wings stick insects) under varying environmental parameters | Delvin | Aims/ Objectives To identify and examine the necessary environmental parameters for ideal growth in Jungle Nymphs, Gray Twigs and Red Wings stick insects Background / Context At present, very little has been understood on the environmental parameters influencing growth rates of captive stick insects as there is a general dearth of available information on the outcomes of captivity of these species. That said, the invertebrate team in the Singapore Zoo has attained remarkable success in the breeding programmes of these three phasmid species and plans to integrate these species into feeder colonies are currently underway (see WNC projects). Therefore, understanding how growth across instar stages as well as physical morphometrics (e.g., length, size) could be positively influenced through controllable environmental parameters could be beneficial for the establishment of such feeder colonies. Methodology To collect data on the morphometric measurements as well as instar changes of phasmids housed under different environmental parameters Expected outcomes Project outcomes can be written into the corresponding chapter for BPGs and LTMPs of each studied species. | 2023-03-01 | Y (for each BPG) | PH (WNC) |  | - Pilots and preliminary studies ongoing - Proposal on-going
| Comparing the use of native browse species to Alfafa hay with captive tortoises housed in TS | Jia Yan / Jon / Sarah | Aims/Objectives To diversify the diets for captive tortoises through the inclusion of relevant browse species (n = 4) Background / Context Alfafa hay (AH) has been a used a mainstay in the diets of captive grazers. Here, the effects stemming from the inclusion of native browse into captive tortoise diet has not been examined even when anecdotal observations have determined that the exclusion of AH led to an increase in frequency and extent of loose stools in the studied species. In addition, the active non-consumption of AH in tortoises has led to a general increase in husbandry man-hours when keepers are required to trim the provided hay into bite-sized portions so as to encourage consumption. Methodology 1. To compare the preferences towards four different browse species across 3 different species of tortoises housed in TS. 2. Activity budgets and levels as well as fecal scores will be recorded Expected outcomes An improvement towards captive tortoise diets in relation to browse provision / availability. |  | Y | PH (WNC) |  | 1. Proposal submitted 2. Data collection started with intern
| Manipulation of UV spectrums to improve the feeding behaviours of Panther chameleons - External collaboration | Jose/Shaun/ NUS | Aims/Objectives To better understand the range of ideal UV spectrums necessary for improved feeding behaviours and patterns in chameleons Background/Context Although information pertaining to ideal UV spectrums have been reported for captive chameleons, the effects of varying UV intensity and wavelengths on feeding behaviour and patterns of Panther chameleons have not been fully established. Here, the study aims to examine how the manipulation of UV spectrums could enhance or improve the feeding behaviour of the studied animals, and how such manipulations could be integrated to improve on the repertoire husbandry procedures for these animals. Methodology To collect observational data on the feeding behaviour and patterns of Panther chameleons under varying levels of UV. Variations in behavioural and health parameters under the influence of varying UV spectrum would be documented. Expected outcomes A better understanding of the importance of UV gradients, and how such manipulations could be supplementary to chameleon husbandry practices | 2023-03-01 | Y |  |  | 1. In-talks with external lab
| The effects of anthropogenic disturbances (e.g., construction) on the bio-acoustics (e.g., calls) of frogs housed in Fragile Forest - External Collaboration | Shaun/Jose/NUS | Aims/Objectives 1. The effects of construction on the frequency and extent of frog calls will be examined 2. Justifying the use of frog calls as an indicator of welfare through correlation with other established amphibian physiological and (i.e., posture, respiration rate) behavioural responses (e.g., stereotypies) Background/Context The development of captive amphibian welfare indicators is at its infancy stages while the notion of frog calls as a response to captive care has not yet been investigated. In this study, the sporadic occurrence of night renovation works (in the absence of park visitorship) provides a unique opportunity to examine the latent effects on frequency and rate of calls as well as the frogs' physiological responses in the following day. Methodology Specialised acoustic equipment (from NUS) will be used to measure the rate and extent of calls of frogs housed in Fragile Forest. Behavioural responses to construction will also be recorded. Expected outcomes A better understanding on the effects of construction on frog behaviour and a new justifiable approach to examining welfare metrics in amphibians. | 2022-03-23 | Y |  |  | 1. In-talks with external lab
Aquatics | Are our Manatee calf growth rates comparable to wild individuals? | Joan/Jayce | Objectives To compare the growth rates of the manatee calves in the wild with those born in River Safari. Using the data collected, we can publish a paper on how we successfully hand-raise our manatee calves in River Safari by monitoring their growth rates. | 2023-03-01 | Y | Guillaume |  | Waiting on Joan to return from Malaysia for discussion / data analysis.
| The fasting cycles of Mekong giant catfishes in River Wonders | Sandra/Jayce | Objectives To better understand the behavioural and morphlogical shifts in MGCs during their endogenous and seasonal fasting cycles Background/Context For the last three years, coarse-scale behavioural responses stemming from the cyclical pattern of inappetance during the monsoon seasons have been documented. In addition to these behavioural changes, an increase in mouth lesions were also observed but not documented. Here, this study aims to better quantify the consequences of such cycles, and its implication to health and husbandry practices. Methodology A fine-scale focal approach to measuring swimming behaviour and scale discolouration will be adopted to quantify the changes induced from in-appetance. Occurrence and extent of mouth lesions will also be rigorously documented. Expected outcome Educational and outreach signages regarding the occurrence of such mouth lesions will be developed to address visitor concerns. Treatment and prevention of such lesions will be discussed with the veterinary department after the project concludes. | 2024-03-01 | Y | Guillaume? |  | 1. Data received from Sandra 2. In-talks of further expansion end of 2022 3. DJ to start data analysis in Aug.
Avian
Carnivores, Small Mammals & Marsupials | The use of olfactory enrichment on the behaviours of two predator species (Red Dhole & Malayan Tiger) | Najilah/Daniel/Cecilia | Objective To study how different olfactory cues can increase the evenness of enclosure spatial use as well as activity levels in dholes and tigers Methodology Ethogram is prepared for both species. Focal + continuous sampling (all-time occurrence) for the 1.1 Malayan Tigers, Instantaneous/scan sampling at fixed time points will be used for the Red Dholes as they are managd in a group setting and focal sampling can be challenging. Olfactory based mixtures for the study include: 1. Feces 2. Blood 3. Catnip Context / Expected Outcomes Both species will be time-sharing the same flex/enclosure in the new Rainforest Park, hence results can be applied to activity and behavioural management considerations, both now and in future. | 2022-03-23 | KIV after discussion and assessment of publication potential with RAP based on data quality | Cecilia | MWG211002 | 25-Nov-21: Data all collected, will liaise with Dr Shangzhe for data analysis and write up
| Mixed exhibits housing small meso-carnivores in Night Safari | Najilah (University Sains Malaysia Msc programme)/Razzak | Objective 1. To examine the social interaction between small predators (e.g., Small Toothed civets, Common Palm civets, Binturong, Masked Palm civet, leopard cat) housed in mixed exhibits 2. To investigate the role of various types of enrichment devices in mediating agonistic interactions betwee small predators Methodology Ethogram will be prepared for all studied species. Context / Expected Outcomes Understanding the dynamics and interactions between small predators under captive care can be highly beneficial for us as we progress towards the Modern Zoo. Here, the outcomes of said study might inform future husbandry practices in relation to installing and maintaining mixed species exhibit, as well as introducing enrichment ideas that are capable of reducing intra- and inter-social aggression.
| Respiratory rate of tree kangaroos in relation to temperature and humidity | Hafiz/Jeff/Joey/Razzak | Objective To study and obtain data on the respiratory rate of the Tree Kangaroos housed in a tropical environment and its correlation with temperature and humidity Context / Expected Outcomes There are not much data on respiration rates of tree kangaroos in publications. As such we would like this study to shed some light on what is the respiration rate of the tree kangaroos in relation to the temperature, humidity as well as in relation to their age, sex and activity. Methodology 1. Ethogram is essential to identify not only the various behavior but also the spatial selection of the exhibit (e.g., how often under shade). 2. A data logger is needed to collect environmental parameters (temperature and humidity) 3. focal sampling with interval recording of respiration rate 4. Temperature of the TKG's ear, body and forearms will also be recorded 5. Data is collected for: - Adult Female (Nupela) - Young male (Malolo) - Adult Male (Makaia) | Mar-23 At least report or write-up | KIV after discussion and assessment of publication potential with RAP based on data quality | Guillaume |  | Ongoing discussion/preparation Should involve other zoos?
Herbivores | Body Condition Scores of Giraffes (External collaboration) | Ivan/Marcus Clausse | A 3-year long project where photographs of the 4.0 giraffes depicting body condition scores are sent to an external collaborator (e.g., Marcus Clausse). | 2025 | Yes, we get co-authorship from this collaborative effort | DJ |  | Ongoing
| Browse preferences in giraffes | Abigail/Indah/Cynthia/Ivan | Aim/Objective 1. To examine the palatability and/or preference of browse species with the 4.0 giraffes in our collection and, 2. To examine how the provision of varying browse types influences their extent of foraging behaviour. Methods A preference and/or palatibility approach to identify preferred browse species will be adapted for the giraffes Ethograms (through ZooMonitor) will be used to examine activity budgets as well as other behavioural indices (e.g., richness, evenness, diversity) Foraging responses will also be measured and documented. Outcomes This study aims to justify the procurement of preferred browse species through observable enhancement and/or improvement in activity levels and patterns following the | 2022-03-01 | N | Guillaume | N/A
Primates | Group dynamics of baboons before and after population management techniques | Boon Kong (BK) | To study the effects of birth control of the group dynamics of our baboon population. To see if the selective management or contraception impacts the breeding behaviours of the dominant animals in their respective harems. Looking to see if docents or VEU can assist in gathering of data. | Will span over 2-3 years Initial phase 1 completion by Nov-21 (intern base line data gathering) | Y Likely as a paper and/or publication under EAZA old world monkey TAG | Claudia |  | Individuals and troops identified in intern's project
| Optimal efficiency of browse intake by leaf-eating primates | Tiara/BK | Aims/Objectives 1. To examine browse palatability and/or preferences with the Proboscis monkey and, 2. To determine the the change in activity levels and patterns following the introduction of preferred browse species. Methods 1. A palatability and/or preference approach to browse species will be conducted following which, 2. ethograms designed to examine changes in activity levels and/or patterns as well as intra-social group interactions (positive and/or negative) will be employed. Outcomes This will help to not only identify the wastages and look towards optimizing our browse provisions but also provide preferred and more nutritious browse species for the animals under our captive care. This is also, in part, supplementary information that could be used to support the nutrition analyses of browse species conducted with WNC. | 2022-02-01 | N Likely in-house presentation | Po-Han |  | Follow up with Po-Han
| The effects of introducing phasmids as feeder insects to Emperor tamarins | Xiao Jun/Kelly/Kumaran | Aims/Objectives 1. To examine palatability and/or preferences of phasmids with the Emperor tamarins and, 2. compare their use to commercial feeder insects (e.g., crickets, mealworms) through changes in behavioural and spatial responses. Methods 1. Ethograms designed to examine changes in activity levels and/or patterns as well as intra-social group interactions (positive and/or negative) following the introduction of phasmids and commercial feeder insects will be used. Outcomes The outcomes of this study is aimed at improving the repertoire of foraging behaviours in Emperor tamarins through the provision of phasmids as feeder insect. In addition, the nutritional analyses of phasmids can be supplementarily used to identify chemical factors that best explains the changes in activity levels and patterns. | 2022-02-01 | N Likely in-house presentation | Po-Han |  | Follow up with Po-Han
| The effects of nightly heat lamps on the diurnal activity patterns and levels of Celebes monkeys | Xiao Jun/Kumaran | Aims/Objectives 1. To examine how the inclusion of heat and/or fog lamps at night could have an effect on the resting behaviour of Celebes monkeys through next-day activity patterns. Methods 1. Ethograms designed to examine the activity levels and patterns of these primates will be used to observe and monitor the studied animals in the exhibit as well as the back of houses. 2. Environmental parameters such as temperature and humidity will also be recorded Outcomes Understanding the influence of heat lamps on sleep cycles or resting behaviour is crucial for manging their next-day activity levels and patterns. The outcomes of this study can and will be used to improve the husbandry procedures related to these primates. | 2023-04-01 |  |  |  | Data collection
| Orangutan Weight-by-age Growth Chart | Xiao Jun/Kumaran | General information on the weights of orangutans is often provided as a range, mostly for the wild counterparts in the adult stage of growth. There is an apparent void of written information on the weight range expected for orangutans at their different stages and years of growth. The analysis of weight data of captive specimens to construct a weight-by-age growth chart will be a helpful tool, especially for the monitoring of health and consequently, welfare of the animals under human care. The chart could work together with data from body condition scoring to help provide a healthy weight range for staff to manage the animals at, building up our knowledge and expertise in caring for these great apes. |  |  | Guillaume |  | Unknown
Wildlife Nutrition Centre | The nutritional analysis of (feeder) insects (e.g., phasmids, blue worms) | Po Han | As part of a inter-disciplinary project, the information obtained from this reseach component will be used to feed in the various projects designed to examine the palatability and/or preference of phasmids / blue worms and the influence these insects have on activity and behavioural patterns.
Wildlife Nutrition Centre | Examining the growth rates of blue worms kept under varying levels of environmental parameters and food type. | Po Han | As part of a inter-disciplinary project, the information obtained from this reseach component will be used to feed in the various projects designed to examine the palatability and/or preference of phasmids / blue worms and the influence these insects have on activity and behavioural patterns.
Giant Panda
Rainforest KidzWorld
Elephants

## FY2122
Animal Care Research Projects FY2122
Section | Project | PI | Context and Expected Outcomes | Expected Completion Date | Publication Expected? (Y/N) | RP Liaison | Accession Number | Status Updates
Wildlife Nutrition Centre | Palatability Study for Callitrichid Diet | Po Han | Feedback from the sections is that the fresh produce is not well accepted by marmosets and tamarins. Therefore, they are not consuming the whole diets proposed by the nutritionist, and it poses concerns that they might be consuming an “unbalanced” diet due to poor palatability. We would like to conduct feeding trails of various fresh produces and check which types are highly accepted. Furthermore, to check how the nutritional composition of new diets change and if it will still meet the recommendations. Based on the results of the study, WNC can then provide fresh produce from the lists with higher palatability when preparing the diets for marmoset and tamarins. As a consequence, they will receive a diet that is mostly consumed by them and also meet their nutritional requirements. The project will be done by WNC interns as it is not very complicated, and no funding is required. | 2021-12-01 | A report will be drafted but publications will depend on how many sample sizes we will be able to collect from sections | Po Han (PI) |  | Need to follow up with Po-Han
Invertebrates | What animals can benefit from BSF larvae as food? | Invert team | - Conduct feeding trials for targeted species in WRS living collection - Assess preference of BSF larvae as invertebrate feeder - Nutritional analysis of BSF larvae (subjected to approval of cos for lab test) | 2022-03-01 | Y | Shangz |  | On-going
| Identifying a new protozoa found in captive butterflies | Delvin/Guillaume/Chiada | - Identify and speciate protozoa | 2022-03-01 | Y | Guillaume & Chiada (PIs) |  | On-going
| Relocation of stingless bee hives | Jagan/Delvin | - Development of matrix to evaluate the stingless bee hive-site preference - Development of hive translocation SOP | 2022-03-01 | Y (Translocation SOP - IUCN)
| Mandai Precinct Butterfly Checklist | Delvin | - Continuous study of butterfly presence to publish MPH’s fist butterfly checklist | 2022-03-01 | Y | Nat
| Assessing butterfly abundance across various flora palettes in Mandai | Delvin | - Evaluation of various sites and presence of butterflies taking into account flora present - Pre and post evaluation of habitat enhancement - Strategy document for Lepidoptera | Progress update - Mar-22 (Project will be continued with more site enhancements) | N
| Jungle Nymph growth rates | Invert team | - Research on development of Jungle nymphs in living collection for BPG | 2022-03-01 | N (Research for BPG)
| Impact of environmental parameters on mortality rate of Giant Prickly | Invert team | - Evaluation of ideal environmental parameters for the maintenance of Giant Prickly Stick Insects in Zoos | 2022-03-01 | Y | Claudia
| First aid guidelines for Invertebrates | Delvin | - Self-explanatory | 2022-03-01 | N | Guillaume |  | Meeting plan for End November/Early December to assess progression
| (KIV) Conservation breeding of Small Cigar Stick Insect – Subjected to NParks approval | Delvin | - To carry out population restoration by reinforcing the existing population in Singapore - Conduct research on the behaviour, biology and survival rates of this species - Promote community awareness of phasmids in Singapore - Develop a feasible model for phasmid reintroduction/reinforcement | KIV | KIV | Nat |  | 25-Nov-21: Presented to Nparks, waiting for official go-ahead
Herpetology | Browse palatability for Batagurs (to concentrate on Batagur trivittata first) | Sarah/Roy | Aims 1. To develop a more suitable and natural diet for Batugur trivittata. 2. To include diet as a chapter of best practice and husbandry guidelines for the species. Description - To assess palatability of browse types and select top 3 for nutritional analysis. - To include browse as part of main diet and assess if BCS and breeding success improves. Methodology - Using epicollect to determine browse consumption/wastage. - Work with WNC to include browse in diet (% and amounts of foods given). - Observe changes in animal behaviour (if any). Expected outcomes - Browse to be fully included as part of diet. - BCS of animals improve. | This is expected to be a long-term study as any BCS changes and breeding will take some time to materialise. Project may extend into the next FY. | Y | Claudia (Better to be Po-Han?) |  | As quite a large part of this is a nutrition study, they will be asking Po-han to do the nutrition analysis, this might make more sense for Po-han to the RP liaison since he will be working with them on this. Also they said the expected completion date will at least be more than a year from now. So this is likely to be in FY23/24. Animals were transferred recently and need to settle in before resuming
| Case Study - Manipulation of temperature to successfully breed Parson's chameleon | Sarah/Shaun | Aims 1. To successfully breed Parson's chameleon in Reptopia (mating and incubation). 2. To include breeding as a chapter of best practice and husbandry guidelines for the species. Description - To assess if artificially controlling the external environment to simulate natural seasonal conditions will increase incidences of courtship behaviour/mating observed between 1.1 individuals. Methodology - Phase 1: Variable to be adjusted: Temperature, to reflect seasonal changes. Observe behaviours of animals. - Phase 2: To see if other factors may be considered (separation of species, exhibit furniture, etc.) Expected outcomes - Successful mating occurs. | All four seasons are required to reflect changing temperatures to initiate the breeding cycle. The project will require a full year to see any potential results. Additionally, if phase 1 is not successful, phase 2 will require re-evaluation of other variables | Y | Claudia |  | This project will start in the next FY22/23 and is expected to be completed in that year. They are currently working on submitting the proposal to RP by March 2022.
| Case Study - Breeding the Golden Mantella (Mantella aurantica) in WRS | Shaun/Jose | Aims 1. To successfully breed the Golden Mantella in Reptopia. 2. To include breeding as a chapter of best practice and husbandry guidelines for the species. Description - To better understand husbandry changes made that has led to the successful breeding of this species. Methodology - Document husbandry practices that lead to successful breeding. Record observations on behaviour, fecundity, reproduction, temperature, humidity, survivorship of offspring (% surviving to adulthood), timeline of life stages. Expected outcomes - Allow for consistent breed on demand programs. | Mar-22 Management of breeding and offspring is already in progress. To gather all required information in the meantime. However, measuring survivorship and timeline of life stages requires a "full lifecycle". Expected to have detailed report by end of FY21/22. | Y - non-scientific | Claudia |  | This project is mainly to write the best practice guidelines so there will be no need for a proposal submitted to RP. As the breeding has halted for now (and probaby for the next year), they cannot confirm their breeding protocol works and hence cannot complete the BPG until the breeding starts again. I estimate the complete date to at least be in FY22/23.
Aquatics | Are our Manatee calf growth rates comparable to wild individuals? | Joan | To compare the growth rates of the manatee calves in the wild with those born in River Safari. Using the data collected, we can publish a paper on how we successfully hand-raise our manatee calves in River Safari by monitoring their growth rates. | 2021-12-31 | Y | Guillaume |  | Follow up with PI
| Developing a structured and effective enrichment program for Manatees | Hafiz | Aim To keep the manatees engaged with their surroundings and improve their psychological and physical well-being with a structured enrichment program and provision of several enrichment devices. This will include water sprinklers, coloured light, puzzle feeders, etc. Methodology A Manatee enrichment calendar will be developed and animal welfare will be assessed before and after implementation of the enrichment program for manatees. Data will be collected and analysed for each enrichment device. Expected outcome With the implementation of the enrichment program, we expect to encourage more natural behaviours and increase the manatees' activity levels. | 2022-06-01 | N | Gail |  | Gail spoke to them in late Nov-21, should be able to complete by Jun-22
Avian | Why captive hornbills (Great Hornbill) don't seal or partially seal nest entrances? | Kimberly | Some captive hornbills have been reported not completely sealing their nest entrances. A literature review will be done and a questionnaire developed for zoos (propose project under EAZA Hornbill TAG) to understand the scope, extent of and hypothesis for this behaviour, and whether this is related to successful breeding in captivity. | 2022-06-01 | Y | Mark |  | Not started yet
| Impact of feeding strategy for Gentoo and King penguin on land versus water on the bird activity budget and body condition | Yanti | The gentoo and king penguins at JBP are currently fed on land even though there is a large water body in their aviary. Keepers will gradually transition into feeding the birds in the water, in preparation for feeding strategies in the new park (where birds will be fed in water). Data will be collected on their activity and body conditions before, during and after this change in feeding strategy, which can be used to improve their management. | 2022-03-01 | Y | Mark | WRS210802 | 25-Nov-21: Now on next step of throwing fish into the water, discussing with Dr Ellen on testing
| Development of standardised tool for evaluation of the feeding strategy for mixed-species exhibit | Nicole | Identifying and analyzing factors affecting food intake in a mixed-species exhibit (such as exhibit size, number of birds, number of species, number of feeding stations and diet types), and developing a tool to determine feeding strategies for mixed-species exhibits based on the results. Data will be collected on food intake (arboreal, terrestrial), food preference of birds (by species) and bird behaviours to form a rubric, which can be further refined into a more sophisticated means for evaluating feeding strategies in mixed-species exhibits. This would ideally provide a standardized method to feed mixed-species exhibits. | 2022-03-01 | Can definitely do presentation; publication depends on results of study | Mark | WRS210702 | 25-Nov-21: Movement of birds, project on hold until population more stable. Prelimary data collected
Carnivores, Small Mammals & Marsupials | Effects on the ethogram of two predator species (Red Dhole & Malayan Tiger) on the use of animal-based olfactory enrichment | Najilah/Daniel | Objective To study how olfactory cues affect predator-prey behaviours with specific focus on Malayan Tiger and Red Dhole. Context / Expected Outcomes Both species will be time-sharing the same flex/enclosure in the new Rainforest Park, hence results can be applied to activity and behavioural management considerations, both now and in future. Methodology Ethogram is prepared for both species. Focal + continuous sampling (all-time occurrence) for the 1.1 Malayan Tigers, Instantaneous/scan sampling at fixed time points will be used for the Red Dholes as they are managd in a group setting and focal sampling is challenging. Olfactory based items for study include: 1. Scent marked logs 2. Scent marked enrichment devices 3. Dry leaves and sand (scent marked) 4. Faeces (after clearing parasite check) | Mar-22 to Apr-22 tentatively, at least report or write-up | KIV after discussion and assessment of publication potential with RAP based on data quality | Cecilia | MWG211002 | 25-Nov-21: Data all collected, will liaise with Dr Shangzhe for data analysis and write up
| Respiratory rate of tree kangaroos in relation to temperature and humidity | Hafiz/Jeff/Felicia | Objective To study and obtain data on the respiratory rate of the Tree Kangaroos in a tropical climate and its correlation with temperature and humidity Context / Expected Outcomes There are not much data on respiration rates of tree kangaroos in publications. As such we would like this study to shed some light on what is the respiration rate of the tree kangaroos in relation to the temperature, humidity as well as in relation to their age, sex and activity. Methodology Ethogram is essential to identify the various behavior when respiration rate is acquired. A data logger is needed to collect environmental parameters focal sampling with interval recording of respiration rate Data is collected for: Adult Female (Nupela) Young male (Malolo) Adult Male (Makaia) | Mar-22 At least report or write-up | KIV after discussion and assessment of publication potential with RAP based on data quality | Guillaume |  | Ongoing discussion/preparation Should involve other zoos?
Herbivores | Developing a training and recalling program for large hoofstock at Singapore Zoo | Hikmat | To develop a training and recalling program for Hoofstock at WRS, including recall, target, station, hand-injection, hoof inspection, voluntary blood draw, ultrasound. Target species Giraffe / Zebra / White Rhino / Nyala / Ostrich | 2022-03-01 | N | Guillaume | N/A | Finalising the plan, will update when ready
Primates | Group dynamics of baboons before and after population management techniques | Boon Kong | To study the effects of birth control of the group dynamics of our baboon population. To see if the selective management or contraception impacts the breeding behaviours of the dominant animals in their respective harems. Looking to see if docents or VEU can assist in gathering of data. | Will span over 2-3 years Initial phase 1 completion by Nov-21 (intern base line data gathering) | Y Likely as a paper and/or publication under EAZA old world monkey TAG | Claudia |  | Individuals and troops identified in intern's project
| Optimal efficiency of browse intake by leaf-eating primates | Julian, Valerie | To determine if the correct browse and foliage is being purchased for our primates. This will help to identify the wastages and look towards optimizing our browse provisions. Currently up to 50% of the browse is unusable either due to low palatability or given in access. Expected outcome is to reduce the amount of wastage to approximately 20%. | 2022-02-01 | N Likely in-house presentation | Po-Han |  | Follow up with Po-Han
| Does feeding the gibbons at a different time affect food intake | Shanice | To study the ideal timing for feedings throughout the day that will result in better consumption and intake of food given to the gibbons. This feeding regime will also help to reduce stress factors, improved welfare, reduce food wastage and provide better usage of manpower. The outcome of this is we will be able to provide more naturalistic timings of when gibbons feed, increased foraging activity and general well-being of the primates. For project support to request to spend some observation times to look and review how the various gibbon species are fed at the other sections. | 2022-04-01 | N Will present a report and likely in-house presentation | Gail |  | Follow up with Shanice
| Orangutan Weight-by-age Growth Chart | Xiao Jun | General information on the weights of orangutans is often provided as a range, mostly for the wild counterparts in the adult stage of growth. There is an apparent void of written information on the weight range expected for orangutans at their different stages and years of growth. The analysis of weight data of captive specimens to construct a weight-by-age growth chart will be a helpful tool, especially for the monitoring of health and consequently, welfare of the animals under human care. The chart could work together with data from body condition scoring to help provide a healthy weight range for staff to manage the animals at, building up our knowledge and expertise in caring for these great apes. | 2022-06-01 | N Generating for in-house reference, can be potentially explored if data is sufficient to be categorized for further analysis. | Guillaume |  | XJ transferred to Chimps
Rainforest KidzWorld | Developing an outreach program using program animals to enhance visitor's awareness of animal welfare | Rusydi/Stefan | Develop an outreach program using the existing and upcoming program animals at RFKW, with a strong messaging on animal care and welfare. This should be followed by a survey to guests that targets at assessing the effectiveness of our messaging and determining how much the guests learn and take home regarding our commitment to animal care and welfare, as well as the importance of welfare itself. | 2022-04-01 | N | Vera |  | Have discussed with Vera
Giant Panda | Giant Panda Vitiligo Project Collaboration | Trisha | This project will be a collaboration between WRS and the CCRCGP to investigate the prevalence of vitiligo in the captive giant panda population (e.g. ‘Kai Kai’s family tree). Simultaneously, we will be assessing whether there are any individuals with vitiligo also showing retinal depigmentation, which can potentially affect eyesight and, consequently, the quality of life of the animal. Waiting for the Chinese to sign the agreement with us. | 2022-03-01 | Y | Shangz |  | Follow up with Trisha
Elephants | Behaviour of elephants before and after PC upgrading works | Syafiqah | Aim To find out the differences in activity budget and welfare for 0.5 elephants when changing from Free Contact Management to Protected Contact Management. Context - Elephants of Asia will be going through Protected Contact upgrading works in the exhibit and the Back Of House area. This will allow the elephant care staff to work safely with the elephants without sharing the same unrestricted space. Methodology - Team will then compare the elephant’s activity budget before, during and after the upgrading works are being made and also when transitioning to Protected Contact Management. - 0.3 elephant’s feces are collected twice a week and are being tested at the Vet Endocrine Lab to check on the cortisol levels. The data will be shared to the Elephant team and will be analyzed with the tally sheet to find out if the transition is affecting the elephant’s welfare. - Data will be collected using point sampling method, individuals identified. We will observe 0.5 elephants with an interval of 30 minutes and 15 minutes (during the Elephant Presentation and Guest Token Feeding sessions). Observation will take place throughout the day. | 2021-12-01 | Y Peer-reviewed publication, case report or presentation | Claudia |  | They are currently reviewing the data

## Research Group
Research Group
Section | Name
Wildlife Nutrition Centre | Po Han
Invertebrates | Delvin
Herpetology | Shaun
Aquatic | Joan, Sandra, Hafiz, Vincent
Avian | Mark, Aaarti, Rachel
Carnivores, Small Mammals & Marsupials | Jeff, Najilah, Daniel, Hafiz, Felicia, Arini, Krystofer, Mohan, Joey, Gladys, Ade, Brynna, Yijun
Herbivores | Abigail
Primates | Boon Kong, Julian, Valerie, Shanice, Kelly, Xiao Jun
Rainforest KidzWorld | Rusydi, Stefan
Giant Panda | Trisha
Elephants | Adil, Syafiqah, Shafiq, Jasbir